## general_report
0.52 Release Closed/Resolved (JIRA)
Displaying 78 issues at 08/Oct/15 11:31 AM.
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date
Bug | OSF-4783 | [Staging] Search is broken - "TypeError: undefined is not an object" | Nici Pfeiffer | Jinlu Yuan | High | Resolved | Fixed | 2015-10-06 12:16 | 2015-10-07 10:16
Bug | OSF-4760 | [Staging and Production] Hotfix: GitHub revisions on OSF just showing the latest version | Natasha Welcher | Amanda Liscouski | High | Resolved | Fixed | 2015-10-05 09:20 | 2015-10-05 10:25
Bug | OSF-4759 | Transaction Middleware Hotfix | Unassigned | Dawn Pattison | High | Resolved | Fixed | 2015-10-05 01:33 | 2015-10-06 14:34
Triage | OSF-4758 | [via OSF] Deactivation Request | Sara Bowman | Sara Bowman | High | Resolved | Fixed | 2015-10-04 13:08 | 2015-10-06 09:16
Triage | OSF-4757 | [via OSF] Deactivation Request | Sara Bowman | Sara Bowman | High | Resolved | Fixed | 2015-10-04 09:06 | 2015-10-06 09:15
Task | OSF-4753 | Regression Test of Archiver | Jinlu Yuan | Nici Pfeiffer | High | Resolved | Fixed | 2015-10-02 16:19 | 2015-10-07 09:34
Bug | OSF-4726 | Super call skipping the parent super method | Unassigned | Larry Banner | Low | Resolved | Fixed | 2015-10-01 14:15 | 2015-10-02 09:56
Improvement | OSF-4707 | Add "choice in" validator for ModularODM fields with restricted options | Unassigned | Andy Boughton | Low | Resolved | Fixed | 2015-09-30 13:53 | 2015-10-02 15:47
Improvement | OSF-4705 | No emails sent when moving or copying files and folders fails | Natasha Welcher | Natasha Welcher | Low | Resolved | Fixed | 2015-09-30 13:02 | 2015-10-01 14:22
Bug | OSF-4702 | fix logs on project mnxva | Steve Loria | Johanna Cohoon | Medium | Resolved | Fixed | 2015-09-30 10:01 | 2015-09-30 10:50
Bug | OSF-4700 | [Safari] Unable to log in | Michael Haselton | Nici Pfeiffer | High | Resolved | Fixed | 2015-09-29 20:32 | 2015-09-30 12:25
Bug | OSF-4689 | Log links to files in Dropbox lead to "Page Not Found" if linked folder is not the root | Natasha Welcher | Natasha Welcher | Low | Resolved | Fixed | 2015-09-29 15:48 | 2015-09-30 12:57
Task | OSF-4678 | Verifying our implementation of the json api schema | Chris Wisecarver | Larry Banner | High | Closed | Done | 2015-09-28 22:35 | 2015-09-29 14:23
Bug | OSF-4672 | Dataverse giving 504 and 500 errors when loading files or connecting an account | Unassigned | Nici Pfeiffer | High | Resolved | Fixed | 2015-09-28 16:04 | 2015-09-30 11:41
Bug | OSF-4671 | Search bar disappears after attempted search and no results are returned | Arpita Ramachandra | Natasha Welcher | Low | Resolved | Fixed | 2015-09-28 15:52 | 2015-10-06 13:55
Improvement | OSF-4666 | How to distinguish top-level nodes? (Discuss) | Unassigned | Steve Loria | Blocker | Resolved | Fixed | 2015-09-28 10:18 | 2015-10-01 11:47
Bug | OSF-4661 | Incorrect word in message on deleted file page | Jinlu Yuan | Jinlu Yuan | Low | Resolved | Fixed | 2015-09-25 17:06 | 2015-10-06 16:29
Bug | OSF-4660 | Pre-data collection registration template needs updated first question | Unassigned | Jinlu Yuan | Low | Resolved | Fixed | 2015-09-25 16:16 | 2015-10-06 16:31
Bug | OSF-4652 | Broken Attributes in NodeContributors causing 500s and badness | Nici Pfeiffer | Fitz Elliott | High | Resolved | Fixed | 2015-09-25 13:33 | 2015-10-02 10:08
Improvement | OSF-4640 | Make user=me work across all appropriate views | Unassigned | Sam Chrisinger | High | Resolved | Fixed | 2015-09-25 11:05 | 2015-09-25 11:31
Bug | OSF-4634 | Requesting files by provider id and not provider type causes a 500 | Fitz Elliott | Chris Wisecarver | Medium | Closed | Done | 2015-09-24 16:35 | 2015-10-02 16:13
Bug | OSF-4629 | Uncaught 500 error when request contains non-dictionary data | Nici Pfeiffer | Dawn Pattison | High | Resolved | Fixed | 2015-09-24 13:10 | 2015-10-05 11:38
Bug | OSF-4624 | Switch fullname to full_name | Unassigned | Sam Chrisinger | High | Resolved | Fixed | 2015-09-24 10:06 | 2015-09-25 14:22
Bug | OSF-4623 | Using the API a user can create a node that has a category other than project, but on the site this is not allowed | Sam Chrisinger | Larry Banner | High | Resolved | Fixed | 2015-09-23 16:42 | 2015-09-24 12:18
Bug | OSF-4622 | Need to fix bugs that raise 500s | Unassigned | Larry Banner | High | Resolved | Fixed | 2015-09-23 16:36 | 2015-09-25 11:41
Task | OSF-4620 | Go/nogo for release 0.51.0 | Unassigned | Steve Loria | Blocker | Resolved | Fixed | 2015-09-23 15:02 | 2015-09-24 22:19
Task | OSF-4619 | Merge prereg-prize-2 into long-lasting centerforopenscience/feature/prereg-prize | Harry Rybacki | Harry Rybacki | Blocker | Closed | Done | 2015-09-23 14:28 | 2015-10-05 15:13
Bug | OSF-4618 | Admins can add contributors to children they are only read+write on | Unassigned | Johanna Cohoon | Critical | Resolved | Fixed | 2015-09-23 12:40 | 2015-09-23 16:20
New Feature | OSF-4608 | [OSF Offline] As an API, I want to know if a file is checked out - and - who checked it out | Chris Seto | Larry Banner | High | Resolved | Fixed | 2015-09-22 15:32 | 2015-09-25 11:01
Task | OSF-4598 | API Security Review & Audit - Sprint 3 | Michael Haselton | Larry Banner | High | Closed | Done | 2015-09-22 12:16 | 2015-10-02 10:03
Task | OSF-4596 | Resolve a question around OSF Offline re: how a user will determine whether he/she has write access to a file/folder | Brian Geiger | Larry Banner | High | Resolved | Fixed | 2015-09-22 11:53 | 2015-10-01 15:27
Task | OSF-4594 | Dealing with User Profile Data | Unassigned | Larry Banner | High | Resolved | Fixed | 2015-09-22 11:02 | 2015-10-01 09:59
Task | OSF-4591 | Dealing with 'Dev-Only' | Larry Banner | Larry Banner | High | Closed | Done | 2015-09-22 10:24 | 2015-10-02 11:16
Task | OSF-4587 | [OSF Offline] As an API, I want to receive error notifications for failed actions | Unassigned | Larry Banner | High | Closed | Done | 2015-09-21 15:17 | 2015-09-22 10:29
New Feature | OSF-4585 | [OSF Offline] As an API, I want to be able to read a timestamp for file/folder | Chris Seto | Larry Banner | High | Resolved | Fixed | 2015-09-21 15:16 | 2015-09-25 08:51
Bug | OSF-4578 | Uncaught ValueError causing 500 when trying to update user profile with blank but not empty fullname | Unassigned | Fitz Elliott | High | Closed | Done | 2015-09-21 13:25 | 2015-10-02 09:49
Bug | OSF-4576 | Review & assess Commenting needs re: APIv2 | Larry Banner | Larry Banner | High | Closed | Done | 2015-09-21 12:51 | 2015-09-25 15:09
Bug | OSF-4573 | [staging & production] Adding an unconfirmed user as an unregistered user to a project sends 2 emails | Unassigned | Nici Pfeiffer | High | Resolved | Fixed | 2015-09-21 12:32 | 2015-09-24 07:56
Bug | OSF-4570 | strip_html needs to handle non-string inputs | Unassigned | Steve Loria | Blocker | Resolved | Fixed | 2015-09-21 11:38 | 2015-09-23 14:17
Bug | OSF-4563 | unconfirmed/deactivated user not blocked via API | Unassigned | Larry Banner | High | Resolved | Fixed | 2015-09-21 10:03 | 2015-09-25 08:30
Bug | OSF-4561 | Fall Epic Sprint 2 0.50.0 Regression Testing | Nici Pfeiffer | Nici Pfeiffer | Low | Resolved | Fixed | 2015-09-21 09:32 | 2015-09-28 15:09
Bug | OSF-4550 | The side navbar on Getting Started page changes size upon scroll and refresh | Unassigned | Wisher Paudel | Low | Resolved | Fixed | 2015-09-18 14:47 | 2015-09-28 09:43
Bug | OSF-4541 | Oauth Architecture Improvements | Steve Loria | Matthew Frazier | Blocker | Resolved | Fixed | 2015-09-17 15:29 | 2015-10-06 15:24
Improvement | OSF-4535 | Move profile_image_url to links | Unassigned | Sam Chrisinger | High | Resolved | Fixed | 2015-09-17 13:21 | 2015-10-06 14:37
Bug | OSF-4513 | Community review of sprint needs | Johanna Cohoon | Johanna Cohoon | High | Closed | Done | 2015-09-17 10:55 | 2015-10-07 09:27
Task | OSF-4503 | .50 - Community review of sprint needs | Johanna Cohoon | Johanna Cohoon | High | Closed | Fixed | 2015-09-17 10:34 | 2015-10-07 19:15
Improvement | OSF-4486 | As a user, I want to render JASP files | Natasha Welcher | Larry Banner | High | Resolved | Fixed | 2015-09-16 15:09 | 2015-09-29 18:12
Bug | OSF-4484 | JSON-API request formatting | Unassigned | Larry Banner | High | Resolved | Fixed | 2015-09-16 14:27 | 2015-10-02 14:49
Bug | OSF-4480 | [MFR] Tabular filtering should be case-insensitive | Unassigned | Matthew Frazier | Low | Resolved | Fixed | 2015-09-16 10:59 | 2015-09-29 13:49
Improvement | OSF-4472 | Need 3rd party guidance for developing OSF Add-ons | Steve Loria | Larry Banner | High | Resolved | Fixed | 2015-09-15 12:04 | 2015-09-24 16:57
Bug | OSF-4466 | [bug] On SHARE page, click on a single name contributor would result in adding an empty filter that prevent events from showing up | Amanda Liscouski | Jiankun Liu | Medium | Resolved | Fixed | 2015-09-14 16:32 | 2015-09-29 18:12
Improvement | OSF-4451 | Dataverse selector gives published option when there is not a published version | Nici Pfeiffer | Nici Pfeiffer | Medium | Closed | Done | 2015-09-11 14:31 | 2015-10-01 10:19
Task | OSF-4449 | Bring up-to-date current Audit/Survey of APIv2 needs in support of OSF | Fitz Elliott | Larry Banner | High | Closed | Done | 2015-09-11 10:49 | 2015-10-02 10:03
Bug | OSF-4434 | Probabilistic Travis build failures | Steve Loria | Steve Loria | Medium | Resolved | Fixed | 2015-09-10 09:49 | 2015-10-06 18:48
Bug | OSF-4429 | Add text to explain merging accounts | Unassigned | Johanna Cohoon | Low | Resolved | Fixed | 2015-09-09 16:28 | 2015-09-24 07:52
Technical Task | OSF-4425 | Identify existing sanitization and escaping methods | Andy Boughton | Andy Boughton | High | Resolved | Fixed | 2015-09-09 15:56 | 2015-10-01 10:58
Bug | OSF-4424 | Box configuration changes cannot be saved | Billy Hunt | Johanna Cohoon | Critical | Closed | Done | 2015-09-09 15:44 | 2015-09-29 15:37
Task | OSF-4420 | Abstract user=me across views | Unassigned | Larry Banner | High | Resolved | Fixed | 2015-09-09 14:56 | 2015-09-25 09:56
Improvement | OSF-4365 | Make file endpoints modifiable | Chris Seto | Brian Geiger | High | Resolved | Fixed | 2015-09-08 10:20 | 2015-09-25 08:51
New Feature | OSF-4360 | Create a Sign up/Create an account page to direct users to the Pre-Reg Challenge workflow | Lyndsy Simon | Erin Mayhood | Critical | Closed | Done | 2015-08-20 10:31 | 2015-10-07 06:45
Improvement | OSF-4337 | Folders misidentified as files in file notification emails | Natasha Welcher | Natasha Welcher | Low | Resolved | Fixed | 2015-09-04 14:17 | 2015-10-05 09:55
Bug | OSF-4329 | Fix Unregistered Users UI issues | Steve Loria | Erin Mayhood | High | Resolved | Fixed | 2015-09-04 11:00 | 2015-09-23 20:12
Improvement | OSF-4320 | Make counts for relationship fields opt-in | Unassigned | Steve Loria | Blocker | Resolved | Fixed | 2015-09-03 16:23 | 2015-09-25 14:24
Improvement | OSF-4306 | Allow making nodes public/private | Unassigned | Steve Loria | High | Resolved | Fixed | 2015-09-03 11:03 | 2015-09-29 21:53
New Feature | OSF-4281 | Remove unused instances from linode | Matt Clark | Matt Clark | Medium | Closed | Done | 2015-09-02 13:41 | 2015-10-06 12:25
Bug | OSF-4263 | Publicly Editable Wiki does not show live edits in Firefox | Sara Taylor | Johanna Cohoon | High | Closed | Done | 2015-09-01 13:29 | 2015-10-08 11:11
Bug | OSF-4257 | Users should show all profile fields in the API | Jinlu Yuan | Larry Banner | High | Resolved | Fixed | 2015-08-31 11:19 | 2015-09-30 12:15
Improvement | OSF-4248 | Improve API Documentation | Natasha Welcher | Larry Banner | High | Resolved | Fixed | 2015-08-28 10:52 | 2015-10-06 12:13
Improvement | OSF-4245 | UI: Mockup new design for meetings | Haoyu Chen | Erin Mayhood | High | Closed | Done | 2015-08-27 16:51 | 2015-09-30 12:38
Bug | OSF-4022 | Improve user-facing error message when editing project titles in prohibited ways | Unassigned | Natasha Welcher | Low | Resolved | Fixed | 2015-08-10 09:36 | 2015-09-30 12:48
Bug | OSF-3830 | Wiki menu - Collapsed menu is taller than expanded menu | Unassigned | Jinlu Yuan | Medium | Resolved | Fixed | 2015-07-23 14:12 | 2015-10-06 13:47
Bug | OSF-3718 | clicking out of project navigation dropdown should close navigation | Unassigned | Johanna Cohoon | Low | Resolved | Fixed | 2015-07-17 14:51 | 2015-09-24 07:47
Bug | OSF-3429 | Download as zip button does not appear for closed folders | Amanda Liscouski | Jinlu Yuan | Medium | Resolved | Fixed | 2015-06-30 11:31 | 2015-09-29 17:28
New Feature | OSF-3428 | [PR - Ready to Review] MFR Share and Embed | Unassigned | Revanth Kolli |  | Resolved | Fixed | 2015-06-30 11:28 | 2015-10-06 14:14
Improvement | OSF-2446 | [PR - feature] multiple personal websites in user profile | Wisher Paudel | Billy Hunt | Blocker | Resolved | Fixed | 2015-04-07 09:39 | 2015-10-02 15:26
Bug | OSF-2141 | [Staging & Production] Profile page obscured view for really long names | Merlin Zhang | Nicole Pfeiffer | Low | Resolved | Fixed | 2015-03-09 10:06 | 2015-09-29 09:23
Improvement | OSF-1006 | Adding users search should include current contributors in the search results | Unassigned | Johanna Cohoon | Blocker | Resolved | Fixed | 2014-09-19 13:40 | 2015-10-05 11:34
Improvement | OSF-1 | Indicate who saved each version of a wiki #318 | Unassigned | Erin Mayhood | Medium | Resolved | Fixed | 2015-07-31 11:24 | 2015-10-07 09:28
Generated at Thu Oct 08 11:31:43 EDT 2015 by Nici Pfeiffer using JIRA 7.0.0-OD-07-011#70107-sha1:db940e9f08514eb8106c402d48bc2e232e7bf7f7.